IMPLEMENTATION PLAN LinkUp — 12-Week Development Roadmap Version 1.0 ¦ Omkar IT Determination ¦ May 2025

| Project | LinkUp — Video Calling & Chat Platform |
| --- | --- |
| Developer | Omkar Chavan — Omkar IT Determination |
| Timeline | 12 Weeks (3 Phases × 4 Weeks) |
| Start Date | Week 1 of June 2025 (suggested) |
| Target Launch | End of August 2025 |
| Methodology | Solo Agile — weekly sprints with self-review |
| Repository | GitHub (private) → Vercel auto-deploy |

# Phase 1 — Foundation (Weeks 1–4)

Goal: Working video call between two users in a shared room. Everything else is scaffolding.

## Week 1 — Project Setup & Room Infrastructure

| Task | Details |
| --- | --- |
| Initialize Next.js 14 project | npx create-next-app@latest linkup --typescript --tailwind --app. Configure ESLint, Prettier. |
| MongoDB Atlas setup | Create M0 free cluster (ap-south-1). Create linkup-prod database. Create rooms, messages, participants collections. |
| Mongoose schemas | Implement Room, Message, Participant schemas with TypeScript interfaces. Add TTL indexes. |
| Environment config | Setup .env.local. Configure Vercel project and link GitHub repo. |
| Deploy skeleton to Vercel | Push empty Next.js app. Confirm auto-deploy pipeline works end-to-end. |
| Landing page (static) | Hero section, feature list, 'Create Room' CTA button. Tailwind CSS. Mobile responsive. |

Week 1 Completion Criteria

Next.js app live on Vercel with custom domain MongoDB Atlas connected and accepting writes Landing page renders correctly on mobile and desktop

## Week 2 — Room Creation & Signaling Server

| Task | Details |
| --- | --- |
| Room creation API | POST /api/rooms/create — generates UUID room ID, saves to MongoDB, returns shareable URL. |
| Room join API | GET /api/rooms/[id] — validates room exists, not expired, not full. Returns room metadata. |
| Socket.io setup | Install socket.io. Create /api/socket endpoint. Handle room:join, room:leave, disconnect events. |
| Room page route | Create /room/[id] page. Fetch room data. Show loading/error states. |
| Host token system | Generate signed JWT on room creation. Store in localStorage. Validate on host-only actions. |
| Room URL share UI | Copy-to-clipboard button with toast notification. QR code display (qrcode.react library). |

Week 2 Completion Criteria

User can create a room and get a shareable URL Second user can navigate to URL and see room data Socket.io server accepts connections and handles room:join/leave

## Week 3 — WebRTC Video Calling

| Task | Details |
| --- | --- |
| Camera/mic access | getUserMedia() with permission UI. Handle browser permission denial gracefully. |
| WebRTC peer connections | RTCPeerConnection setup. SDP offer/answer flow via Socket.io signaling. |
| ICE candidate exchange | signal:ice Socket.io events. STUN config: stun.l.google.com:19302. |
| Video grid UI | CSS Grid layout for participant videos. Self-view in corner. Responsive for 2–10 participants. |
| simple-peer integration | Simplify WebRTC connection lifecycle. Handle peer join/leave dynamically. |
| Multi-peer mesh topology | Each participant connects directly to every other participant (mesh). Max 10 users. |

Week 3 Completion Criteria

Two browser tabs on same machine can see and hear each other via WebRTC Three participants can join same room and all see each other Video grid adjusts layout based on participant count

## Week 4 — Controls & Real-Time Chat

| Task | Details |
| --- | --- |
| Participant controls | Mute/unmute toggle. Camera on/off. UI indicators for muted/video-off state. |
| Host controls | Mute all. Kick participant (emit control:kick, trigger disconnect on target client). |
| Real-time chat panel | Slide-in chat panel. Socket.io chat:message broadcast. Message list with sender name + timestamp. |
| Chat persistence | Save messages to MongoDB messages collection. Fetch history on room join. |
| Presence indicators | Online/Away/In-Meeting status. Update on window blur/focus events. |
| Phase 1 testing | Test on Chrome, Firefox, Safari. Test on mobile browser. Fix WebRTC issues found. |

Phase 1 Done — Milestone Checkpoint

Full video call works between 2–5 participants Real-time chat works with history Host controls functional App live on Vercel, shareable with real users All tests passing on Chrome, Firefox, Safari

# Phase 2 — Enhanced Features (Weeks 5–8)

Goal: Add the features that differentiate LinkUp from basic video call tools.

## Week 5 — Screen Sharing & Encryption Layer

| Task | Details |
| --- | --- |
| Screen sharing | getDisplayMedia() API. Replace video track in peer connections when sharing starts/stops. |
| Screen share UI | Shared screen occupies main area. Participants move to sidebar strip. |
| DTLS-SRTP verification | Confirm WebRTC connections are using SRTP. Log in chrome://webrtc-internals. |
| TURN server setup | Deploy Coturn on Render free tier. Configure with username/password auth. Test fallback path. |
| Room password protection | Add password field to room creation. bcrypt hash stored in MongoDB. Prompt on join. |
| Connection quality indicator | RTCPeerConnection.getStats() — show signal strength icon per participant. |

## Week 6 — Reactions, Waiting Room & Expiry

| Task | Details |
| --- | --- |
| Emoji reactions | Reaction picker UI. reaction:send Socket.io event. Floating emoji animation overlay using CSS keyframes. |
| Waiting room | Participants enter waiting state. Host sees list and approves/denies each. Socket.io approval flow. |
| Room expiry system | MongoDB TTL on rooms. Server-side check on join. Client redirect when room expires. Countdown timer in UI. |
| Hand raise indicator | Toggle hand-raise status. Visible icon on participant video. Sorted to top of participant list. |
| Notification sounds | Subtle Web Audio API tones for: join, leave, new chat message, hand raise. |

## Week 7 — File Sharing & Whiteboard

| Task | Details |
| --- | --- |
| File sharing | Drag-and-drop to chat panel. Store in MongoDB (files under 16MB as GridFS, or base64 for small files). Shared as download link. |
| File expiry | 24-hour TTL on shared files. Auto-delete from MongoDB. |
| Whiteboard | HTML5 Canvas. Socket.io sync for draw events (path coordinates broadcast in real time). Clear/undo controls. |
| Whiteboard permissions | Host can open/close whiteboard. All participants can draw by default (configurable). |

## Week 8 — Custom Rooms & Recording

| Task | Details |
| --- | --- |
| Custom room names | Vanity URL: /room/my-team-name. Slugify input, check uniqueness in MongoDB. Fallback to UUID if taken. |
| Local recording | MediaRecorder API. Record local video+audio stream. Download as .webm on stop. No server storage. |
| Recording UI | Record button with red indicator. Timer display. Stop + download prompt. |
| Phase 2 testing | End-to-end test all new features. Load test with 8+ participants. Fix issues. |

Phase 2 Done — Milestone Checkpoint

Screen sharing, reactions, waiting room, file sharing all functional TURN server fallback tested and working Custom room names working Local recording functional

# Phase 3 — Polish, SEO & Launch (Weeks 9–12)

Goal: Production-ready. Real users. Feedback loop running.

## Week 9 — UI Polish & Accessibility

| Task | Details |
| --- | --- |
| Dark mode | Tailwind dark: classes. Persist preference in localStorage. |
| Responsive refinement | Test and fix UI on mobile (iOS Safari, Android Chrome). Video controls accessible with thumb. |
| Accessibility | Keyboard navigation for all controls. ARIA labels. Focus management. Screen reader test. |
| Loading states | Skeleton loaders for room join. Spinner during WebRTC negotiation. Error states with retry. |
| Onboarding tooltips | First-time user tips: 'Click to share your link', 'You are the host'. Dismissible. |

## Week 10 — SEO, Analytics & Performance

| Task | Details |
| --- | --- |
| SEO setup | Next.js Metadata API. OG tags for room share links (room name + participant count in preview). Sitemap.xml. |
| Vercel Analytics | Enable Vercel Web Analytics (free). Track: page views, room creation rate, session duration. |
| Performance audit | Lighthouse audit. Target: 90+ Performance, 100 Accessibility. Optimize images, bundle size. |
| MongoDB query optimization | Add missing indexes. Review slow queries with Atlas query profiler. |
| Error monitoring | Vercel error logs + custom error boundary in React. Log WebRTC failures to console + MongoDB. |

## Week 11 — Beta Testing & Bug Fixes

| Task | Details |
| --- | --- |
| Beta user recruitment | Invite 20–30 friends, college peers, clients. Share testing guide. |
| Cross-browser testing | Structured test matrix: Chrome/Firefox/Safari/Edge × Windows/Mac/Android/iOS. |
| Network condition testing | Test on slow 3G (Chrome DevTools throttling). Test behind VPN. Test TURN fallback. |
| Bug triage | Categorize bugs: P1 (blocks usage), P2 (degrades UX), P3 (cosmetic). Fix all P1s before launch. |
| Feedback collection | Google Form for beta feedback. 10-question usability survey. NPS score collection. |

## Week 12 — Launch

| Task | Details |
| --- | --- |
| Production checklist | All env vars set in Vercel. MongoDB indexes confirmed. TURN server healthy. Custom domain with SSL. |
| Launch announcement | LinkedIn post. Instagram reel demo (@omkar_it_determination). Product Hunt submission. |
| Documentation | Basic /help page with FAQ. WebRTC troubleshooting guide (common issues + fixes). |
| Monitoring setup | Vercel uptime alerts. MongoDB Atlas alerts for storage > 400MB. Manual daily check week 1. |
| Post-launch feedback loop | Check analytics daily. Respond to user feedback within 24 hours. Weekly bug fix release cadence. |

# Kill Switch Criteria

Pivot or stop if any of the following are true by end of Month 3:

When to pivot or kill the project

- WebRTC connection success rate < 80% — signaling or TURN server architecture needs rebuild - < 50 unique users after 6 weeks of being live — validate problem-solution fit before adding features - MongoDB M0 storage exhausted in < 60 days — monetize or purge strategy failing - Solo dev cannot maintain quality above Phase 2 — reduce scope, don't ship broken features - Vercel bandwidth limit hit consistently — need to evaluate paid plan ROI or architecture change

# Summary Timeline

| Phase | Weeks | Key Deliverables |
| --- | --- | --- |
| Phase 1 — Foundation | 1–4 | Room creation, WebRTC video, real-time chat, host controls. App live on Vercel. |
| Phase 2 — Features | 5–8 | Screen share, encryption, reactions, waiting room, file sharing, whiteboard, recording. |
| Phase 3 — Launch | 9–12 | UI polish, SEO, analytics, beta testing, production launch, feedback loop. |

| Total Duration | 12 Weeks |
| --- | --- |
| Total Developer Days | ~60 working days (solo) |
| Infrastructure Cost at Launch | $0/month |
| Launch Target | End of August 2025 |